## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43035 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Identfying and defining the problems | 2017-10-27 | 2017-11-01 | 4 | 5 | 0 | 100%
Basic Conceptual Design | 2017-11-01 | 2017-11-11 | 10 | 10 | 0 | 100%
Creating bill of materıals | 2017-11-09 | 2017-11-11 | 2 | 2 | 0 | 100%
Procuring Components | 2017-11-11 | 2017-11-18 | 7 | 0 | 7 | 0%
Gathering theoretical knowledge about components | 2017-11-11 | 2017-11-18 | 7 | 0 | 7 | 0%
Component testing | 2017-11-18 | 2017-11-23 | 5 | 0 | 5 | 0%
Effectiveness of components evaluated | 2017-11-22 | 2017-11-25 | 3 | 0 | 3 | 0%
Eliminating sub par components | 2017-11-23 | 2017-11-26 | 3 | 0 | 3 | 0%
Module conceptual design | 2017-11-21 | 2017-11-26 | 5 | 0 | 5 | 0%
Image processing algorithm | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Control algorithm | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Motors and drivers | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Interfacing microcontroller and microprocessor | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Power system | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Chassis | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Visibility marks and flags | 2017-11-26 | 2017-12-10 | 14 | 0 | 14 | 0%
Testing and design revisions of modules | 2017-11-28 | 2017-12-10 | 12 | 0 | 12 | 0%
Final testing of submodules | 2017-12-10 | 2017-12-18 | 8 | 0 | 8 | 0%
Documentation | 2017-12-10 | 2017-12-18 | 8 | 0 | 8 | 0%
Setting standards | 2017-11-11 | 2017-12-01 | 20 | 0 | 20 | 0%
Demo of submodules | 2017-12-18 | 2017-12-22 | 4 | 0 | 4 | 0%
Conceptual design report | 2017-12-23 | 2017-12-27 | 4 | 0 | 4 | 0%
Presentation of modules | 2018-01-02 | 2018-01-07 | 5 | 0 | 5 | 0%
Working on modules and combining in winter break | 2018-01-20 | 2018-02-11 | 22 | 0 | 22 | 0%
Theoretical and analytical work on the design | 2018-02-12 | 2018-03-07 | 23 | 0 | 23 | 0%
Testing and improving the product | 2018-02-18 | 2018-03-06 | 16 | 0 | 16 | 0%
Finalizing the design theoretically | 2018-03-07 | 2018-03-13 | 6 | 0 | 6 | 0%
Critical design report | 2018-03-11 | 2018-03-14 | 3 | 0 | 3 | 0%
Practically implementing the modules together | 2018-03-15 | 2018-04-27 | 43 | 0 | 43 | 0%
Testing and solving problems | 2018-03-18 | 2018-04-27 | 40 | 0 | 40 | 0%
Necessary documentations | 2018-04-17 | 2018-04-26 | 9 | 0 | 9 | 0%
Finalizing the product for implementation | 2018-04-28 | 2018-05-02 | 4 | 0 | 4 | 0%
Final Report | 2018-05-10 | 2018-05-16 | 6 | 0 | 6 | 0%
Demonstrating to the jury (customer) | 2018-06-05 | 2018-06-07 | 2 | 0 | 2 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.