## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43157 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Detecting 7 Segment with Raspberry | 2018-02-26 | 2018-03-03 | 7 | 5 | 0 | 100%
Getting Distance Info with Raspberry | 2018-02-26 | 2018-03-05 | 7 | 7 | 0 | 100%
Getting Orientation Info with Raspberry | 2018-02-26 | 2018-03-05 | 7 | 7 | 0 | 100%
Building the robot with new Chassis | 2018-02-26 | 2018-03-05 | 7 | 0 | 7 | 0%
Detecting IR flags | 2018-03-03 | 2018-03-06 | 3 | 0 | 3 | 0%
Transmitting IR flags | 2018-03-03 | 2018-03-06 | 3 | 0 | 3 | 0%
Robot Maneuvers (Leaving. Rejoining) | 2018-03-05 | 2018-03-08 | 3 | 0 | 3 | 0%
Interfacing microprocessor and microcontroller | 2018-03-05 | 2018-03-08 | 3 | 0 | 3 | 0%
Control algorithm | 2018-03-05 | 2018-03-12 | 7 | 0 | 7 | 0%
Practically implementing the modules together | 2018-03-07 | 2018-03-10 | 3 | 0 | 3 | 0%
Testing and solving problems | 2018-03-07 | 2018-03-21 | 14 | 0 | 14 | 0%
Finalizing the design | 2018-03-26 | 2018-04-09 | 14 | 0 | 14 | 0%
Critical design report | 2018-03-06 | 2018-03-09 | 3 | 0 | 3 | 0%
Finalizing the product for implementation | 2018-04-25 | 2018-05-09 | 14 | 0 | 14 | 0%
Final Report | 2018-05-01 | 2018-05-05 | 4 | 0 | 4 | 0%
Demonstrating to the jury (customer) | 2018-05-14 | 2018-05-18 | 4 | 0 | 4 | 0%
0%
0%
0%
0%
0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.